## Sheet1
Simone Davison
Start Time | End Time | Time Spent | Total time | Quick summary of work
2021-10-06 15:00 | 2021-10-06 16:00 | 1:00 | 1:00 | Team meeting - get to know everyone and discuss our visions for the project. With Austin and Andrew
2021-10-08 16:00 | 2021-10-08 16:30 | 0:30 | 1:30 | Customer meeting - met with Jagodzinski to get aquainted and learn about the project. With Austin
2021-10-10 11:50 | 2021-10-10 12:10 | 0:20 | 1:50 | Cloned project, looked at files, and started time log
2021-10-11 15:40 | 2021-10-11 16:00 | 0:20 | 2:10 | Team meeting - assingned tasked, set up weekly meet up times. With Andrew and Austin
2021-10-13 15:00 | 2021-10-13 15:50 | 0:50 | 3:00 | Team meeting - customer expectations and brainstormed ideas for the customer meeting. With Austin
2021-10-14 12:50 | 2021-10-14 13:30 | 0:40 | 3:40 | Customer meeting - shared ideas for the project, discussed security risks, solidified customer needs. With Andrew
2021-10-18 15:30 | 2021-10-18 16:30 | 1:00 | 4:40 | Team meeting - Discussed vision and scope documents. With Austin and Andrew
2021-10-25 08:15 | 2021-10-25 08:55 | 0:40 | 5:20 | Research - Finding libraries for voice recognition
2021-10-25 10:00 | 2021-10-25 11:50 | 1:50 | 7:10 | Vision&Scope - Scope and Limitations Document
2021-10-25 12:05 | 2021-10-25 12:50 | 0:45 | 7:55 | Vision&Scope - Peer Reviewing
2021-10-28 10:30 | 2021-10-28 11:10 | 0:40 | 8:35 | Vision&Scope - Scope and Limitations Document
2021-10-28 12:00 | 2021-10-28 13:30 | 1:30 | 10:05 | Team meeting & Customer meeting - finishing V&S
2021-10-28 13:30 | 2021-10-28 15:00 | 1:30 | 11:35 | Vision&Scope - Deliverables
2021-11-01 10:00 | 2021-11-01 12:20 | 2:20 | 13:55 | Vision&Scope - Finishing
2021-11-08 10:00 | 2021-11-08 12:10 | 2:10 | 16:05 | Research - Finding libraries for voice recognition
2021-11-10 14:00 | 2021-11-10 15:00 | 1:00 | 17:05 | Team meeting - with Andrew and Austin
2021-11-11 21:40 | 2021-11-11 22:10 | 0:30 | 17:35 | Organized repo and added video clips
2021-11-14 13:00 | 2021-11-14 16:00 | 3:00 | 20:35 | Team meeting - Worked on proof of concept with Andrew and Austin
2021-11-20 16:00 | 2021-11-20 17:30 | 1:30 | 22:05 | Worked on SRS
2021-11-21 13:00 | 2021-11-21 14:00 | 1:00 | 23:05 | Worked on SRS
2021-11-21 18:00 | 2021-11-21 23:15 | 5:15 | 28:20 | Worked on SRS, peer reviewed, and added sequence diagrams
2021-11-22 10:00 | 2021-11-22 10:40 | 0:40 | 29:00 | Worked on SRS - fixed formatting
2021-12-02 11:00 | 2021-12-02 12:10 | 1:10 | 29:30 | Milestone1 - finished and turned in with Andrew and Austin
Winter W1
2022-01-06 10:00 | 2022-01-06 12:00 | 2:00 | 2:00 | Team meeting - Discuss upcoming assingments and prep for customer meeting
2022-01-06 12:00 | 2022-01-06 12:15 | 0:15 | 2:15 | Customer meeting - Shared info and prepped for the quarter
2022-01-06 12:15 | 2022-01-06 12:45 | 0:30 | 2:45 | Team meeting - wrote up Initial Customer Contact document with Austin
2022-01-07 15:00 | 2022-01-07 16:00 | 1:00 | 3:45 | Team meeting - discussed recording sessions and flyer with Andrew and Austin
2022-01-07 16:25 | 2022-01-07 16:50 | 0:25 | 4:10 | Drafting info gathering questions for recording sessions
2022-01-11 14:00 | 2022-01-11 16:10 | 2:10 | 6:20 | Finish Quarter Plan and Testing Plan and work on CSV reader
Winter W2
2022-01-13 12:00 | 2022-01-13 13:00 | 1:00 | 1:00 | Customer meeting, team checkin, and posted meeting notes
2022-01-13 13:30 | 2022-01-13 17:35 | 4:05 | 5:05 | Getting programs to work on my setup. Tested splitter.py zoomvid videos
2022-01-17 14:30 | 2022-01-17 15:50 | 1:20 | 6:25 | Team meeting - discussed video content
2022-01-17 21:35 | 2022-01-17 22:50 | 1:15 | 7:40 | Drafting up emails for class pictures
Winter W3
2022-01-21 10:30 | 2022-01-21 11:00 | 0:30 | 0:30 | Meeting with Customer and submitting meeting notes
2022-01-24 14:00 | 2022-01-24 15:30 | 1:30 | 2:00 | Emails, and recording videos with Austin
2022-01-25 14:00 | 2022-01-25 17:05 | 3:05 | 5:05 | Emails, and group meeting, work on weaver.py
Winter W4
2022-01-27 09:30 | 2022-01-27 11:35 | 2:05 | 2:05 | Work on weaver.py to stitch together the demo video
2022-01-27 12:00 | 2022-01-27 12:20 | 0:20 | 2:25 | Customer meeting
2022-01-27 12:30 | 2022-01-27 13:30 | 1:00 | 3:25 | Group meeting - milestone 2
2022-02-02 11:30 | 2022-02-02 12:00 | 0:30 | 3:55 | Brain storming - video content
Winter W5
2022-02-03 12:00 | 2022-02-03 12:15 | 0:15 | 0:15 | Client meeting
2022-02-07 14:00 | 2022-02-07 14:50 | 0:50 | 1:05 | Recoring session and tested boom mic
2022-02-08 14:00 | 2022-02-08 16:25 | 2:25 | 3:30 | Working on firebase and recording session
2022-02-09 10:40 | 2022-02-09 12:15 | 1:35 | 5:05 | Firebase - setting up the DB, revising the content collection plan
Winter W6
2022-02-10 12:00 | 2022-02-10 12:15 | 0:15 | 0:15 | Client meeting
2022-02-10 12:20 | 2022-02-10 13:30 | 1:10 | 1:25 | Milestone 3
2022-02-14 14:00 | 2022-02-14 15:20 | 1:20 | 2:45 | Recording session and meeting
2022-02-15 15:00 | 2022-02-15 16:00 | 1:00 | 3:45 | Recording session and meeting
2022-02-16 11:00 | 2022-02-16 11:55 | 0:55 | 4:40 | Work on weaver.py to access the database
2022-02-16 14:10 | 2022-02-16 14:35 | 0:25 | 5:05 | Work on weaver.py to access the database
Winter W7
2022-02-17 12:00 | 2022-02-17 12:15 | 0:15 | 0:15 | Client meeting
2022-02-22 14:15 | 2022-02-22 16:25 | 2:10 | 2:25 | Group meeting, recording session, and working on creating videos
2022-02-23 10:50 | 2022-02-23 12:10 | 1:20 | 3:45 | Working on video weaver to upload and download files
Winter W8
2022-02-23 21:15 | 2022-02-23 23:25 | 2:10 | 2:10 | Working on video weaver to upload and download files
2022-02-24 12:00 | 2022-02-24 12:15 | 0:15 | 2:25 | Client meeting with a demo
2022-02-24 13:15 | 2022-02-24 13:55 | 0:40 | 3:05 | MS4
2022-02-28 14:00 | 2022-02-28 15:50 | 1:50 | 4:55 | Recording session, team meeting, and work on accessing storage
2022-03-01 14:00 | 2022-03-01 16:05 | 2:05 | 7:00 | Recording session, team meeting, and get weaver to work with new database and finish implementing CSV reading
Winter W9
2022-03-03 10:30 | 2022-03-03 11:30 | 1:00 | 1:00 | Integrate CSV reading into weaver
2022-03-03 12:00 | 2022-03-03 12:15 | 0:15 | 1:15 | Client meeting
2022-03-07 14:50 | 2022-03-07 15:30 | 0:40 | 1:55 | Working on weaver to collect videos for weaving.
2022-03-08 15:00 | 2022-03-08 15:30 | 0:30 | 2:25 | Working on weaver to collect videos for weaving.
2022-03-09 10:15 | 2022-03-09 12:00 | 1:45 | 4:10 | Working on weaver to collect videos for weaving.
Winter W10
2022-03-10 09:45 | 2022-03-10 11:20 | 1:35 | 1:35 | Migrating functions to a new file and getting the weaver to use storage access functions
2022-03-10 12:00 | 2022-03-10 14:15 | 2:15 | 3:50 | Client meeting, MS5, working on presentation
2022-03-11 10:05 | 2022-03-11 12:30 | 2:25 | 6:15 | Work on weaver to get it to a point where it can do a full run through
Total hours Winter 2022
54:20
Spring W1
2022-04-01 12:35 | 2022-04-01 16:15 | 3:40 | 3:40 | Messing with multiprocessing, Team meeting, and client meeting
2022-04-03 16:05 | 2022-04-03 18:05 | 2:00 | 5:40 | Messing with multiprocessing (made some good headway)
2022-04-03 18:40 | 2022-04-03 20:15 | 1:35 | 7:15 | Messing with multiprocessing (came across a different approach I wanted to try)
2022-04-04 13:00 | 2022-04-04 15:30 | 2:30 | 9:45 | Get program to read excel files (pair programmed with Austin)
2022-04-05 12:40 | 2022-04-05 13:20 | 0:40 | 10:25 | Get program to read excel files (success!)
Spring W2
2022-04-08 13:05 | 2022-04-08 13:50 | 0:45 | 0:45 | Implementing excel reading and multiprocessing to weave.py
2022-04-08 14:00 | 2022-04-08 14:15 | 0:15 | 1:00 | client meeting
2022-04-08 14:25 | 2022-04-08 15:05 | 0:40 | 1:40 | Implementing excel reading and multiprocessing to weave.py
2022-04-10 17:15 | 2022-04-10 18:20 | 1:05 | 2:45 | Implementing excel reading and multiprocessing to weave.py (isolating weaving into its own function can converting both CSV and XLSX to pass in list)
2022-04-13 12:40 | 2022-04-13 14:35 | 1:55 | 4:40 | Implementing excel reading and multiprocessing to weave.py (Re adding passing in commandline args and testing)
Spring W3
2022-04-15 14:00 | 2022-04-15 14:15 | 0:15 | 0:15 | client meeting
2022-04-18 14:45 | 2022-04-18 15:55 | 1:10 | 1:25 | Test weave function and integration test
2022-04-19 17:45 | 2022-04-19 20:25 | 2:40 | 4:05 | Debug weave.py to begin writing videos again (forgot to actualy enter start time of my start time so it is an estimate)
2022-04-20 14:30 | 2022-04-20 14:50 | 0:20 | 4:25 | client meeting
Spring W4
2022-04-25 19:50 | 2022-04-25 21:45 | 1:55 | 1:55 | Collecting dependencies, and researching making an executable.
2022-04-26 12:10 | 2022-04-26 16:15 | 4:05 | 6:00 | Testing program on lab computers, dubugged, and worked with Austin a bit
Spring W5
2022-04-29 12:35 | 2022-04-29 15:35 | 3:00 | 3:00 | Debugging program on lab machines and making processes go from using 2 folders to 1 folder each. + client and team meeting
2022-04-30 13:45 | 2022-04-30 16:10 | 2:25 | 5:25 | Debugging program on lab machines. Fixed multiproc error (with only pinging fb once), added try catch for grad years, and organized donor files.
2022-05-01 16:05 | 2022-05-01 19:00 | 2:55 | 8:20 | Debugging program on lab machines: Fixed upload bug, added clean up methods, and fixed a loop that prevented processes from moving on.
2022-05-02 12:10 | 2022-05-02 16:40 | 4:30 | 12:50 | Get image creation and writing to work with Pillow. Success and moved into weave.py
Spring W6
2022-05-06 12:00 | 2022-05-06 21:40 | 9:40 | 9:40 | Trying to fix the mp bug that said queue full. Splitting data first into files, then each process gets a file and appends urls, after all are done, merge. Still not fixed, but better. Also went to the client meeting.
2022-05-11 12:45 | 2022-05-11 14:30 | 1:45 | 11:25 | FORGOT TO ADD START TIME: researching multiproc bug, work on weave.py: added try catch, updated text, and debugged appending to temp row files
Spring W7
2022-05-11 21:35 | 2022-05-11 23:55 | 2:20 | 2:20 | Mending binary appending bug. Refining text. Refining Video content.
2022-05-12 14:00 | 2022-05-12 15:00 | 1:00 | 3:20 | Recorded more videos.
2022-05-13 14:00 | 2022-05-13 14:15 | 0:15 | 2:35 | Customer meeting
2022-05-16 12:45 | 2022-05-16 13:40 | 0:55 | 3:30 | Changing text, going over clips, testing save data on crash, and adding WWU font
2022-05-16 14:30 | 2022-05-16 15:25 | 0:55 | 4:25 | (FORGOT TO ADD START TIME) Merged two excel files and verified data was not lost
2022-05-16 18:25 | 2022-05-16 21:25 | 3:00 | 7:25 | Fixing final donor file, centering text in videos, and fixed text to account for graduating less than a year ago
2022-05-17 11:30 | 2022-05-17 13:50 | 2:20 | 9:45 | Continuing to look at multiprocessing bug on lab machines.
2022-05-17 14:00 | 2022-05-17 14:15 | 0:15 | 10:00 | Client meeting
2022-05-17 14:30 | 2022-05-17 15:00 | 0:30 | 10:30 | Recorded more videos.
Spring W8
2022-05-18 20:00 | 2022-05-18 23:20 | 3:20 | 3:20 | (Forgot to add start time) Lengthing music, handling spaces in names, making some videos, and isolating remaining donors after crash.
2022-05-19 18:00 | 2022-05-19 20:00 | 2:00 | 5:20 | (Forgot to add) Reasearching audio bug on IOS phones and tablets
2022-05-20 12:00 | 2022-05-20 13:55 | 1:55 | 7:15 | Actually trying to fix the IOS audio bug. If sucessful, rewrite all the audios.
2022-05-20 14:00 | 2022-05-20 14:20 | 0:20 | 7:35 | Client meeting
2022-05-20 14:30 | 2022-05-20 15:55 | 1:25 | 9:00 | Implementing mass audio conversion - Success! All videos now have audio that works on IOS!
2022-05-20 20:30 | 2022-05-20 21:00 | 0:30 | 9:30 | Reimplementing audio conversion solution since it got lost. Not needed, but I still want it.
Spring W9
2022-05-31 13:45 | 2022-05-31 15:45 | 2:00 | 2:00 | Clean code and work on documentation
2022-05-31 21:00 | 2022-05-31 22:00 | 1:00 | 3:00 | Clean code and work on documentation
Total hours Spring 2022
73:45